## Use Cases
UC | The use case | Expected behaviour | Pass / Fail | Actual behaviour / Current behaviour | Actor | Module | Source | Test Type | API / Screen | Steps Performed | Severity | Notes
UC-001 | User Login | POST /api/v1/auth/login with valid credentials returns access + refresh tokens, role claims, and routes user to role-appropriate landing page (SYSTEM_ADMIN→/home, OPS_USER→/loan-applications, PRODUCT_ADMIN→/products, LSP→/my-loans). | Pass | Fresh Newman verified admin login 200 with access token and LSP UI login 200; Playwright used authenticated UI session. | All human users | Authentication | PDF + code | API | POST /api/v1/auth/login + /login UI | POST /auth/login; Playwright storage-state login |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-002 | Mandatory Password Change | After login when must_change_password=true, user is redirected to /change-password; POST /api/v1/auth/password updates password, clears flag, allows normal access. | Pass | Password reset flow verified: reset login returned passwordChangeRequired=True and helper completed password change. | Authenticated user | Authentication | PDF + code | API | POST /api/v1/auth/password + /change-password UI | POST /users/{id}/reset-password + POST /auth/password |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-003 | Session Refresh and Logout | POST /auth/refresh renews access token without re-credentialing; POST /auth/logout invalidates refresh token and clears session. | Needs Verification | Logout returned 204, but refresh-token renewal and refresh invalidation were not independently re-tested. | All human users | Authentication | PDF + code | API | POST /api/v1/auth/refresh, POST /api/v1/auth/logout | POST /auth/logout; refresh path still required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-004 | API Client Token Issuance | POST /api/v1/auth/token with valid client_id+secret returns scoped JWT (tenant=lsp_id, role=LSP_API_CLIENT). Inactive client, inactive LSP, or IP allowlist violation returns 401/403. | Pass | LSP API client token exchange returned 200 and bearer token. | LSP API Client | Authentication | PDF + code | API | POST /api/v1/auth/token | POST /api/v1/auth/token |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-005 | View Session Context | GET /api/v1/internal/system/context returns {userId, username, roles[], lspId?, tenantScope} for authenticated user. | Pass | System context returned 200 with SYSTEM_ADMIN role. | All authenticated humans | Session | PDF + code | API | GET /api/v1/internal/system/context | GET /api/v1/internal/system/context |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-006 | Create LSP Tenant | POST /api/v1/internal/admin/lsps (SYSTEM_ADMIN) creates inactive LSP record; new id is then available for product mappings, users, API clients, webhook config. | Pass | Created LSP tenant and listed it successfully in admin LSP list. | System Administrator | LSP Admin | PDF + code | API | POST /api/v1/internal/admin/lsps + /lsps UI | POST /admin/lsps; GET /admin/lsps |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-007 | Activate or Deactivate LSP | PUT /lsps/{lspId}/status flips LSP status; deactivation cascades to API clients (disabled) and blocks LSP API/UI access. | Needs Verification | Inactive LSP token denial was verified, but full activate/deactivate cascade and UI/API kill-chain were not re-tested end-to-end. | System Administrator | LSP Admin | PDF + code | API | PUT /api/v1/internal/admin/lsps/{lspId}/status | Needs full PUT /lsps/{id}/status scenario |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-008 | Configure LSP Webhook Subscription | PUT /lsps/{lspId}/webhook-subscription persists endpoint URL + secret + event subscriptions; future domain events for that LSP enqueue in webhook_event_outbox. | Pass | Webhook subscription update returned 200 for fresh LSP. | System Administrator | Webhooks | PDF + code | API | PUT /api/v1/internal/admin/lsps/{lspId}/webhook-subscription | PUT /admin/lsps/{id}/webhook-subscription |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-009 | Manage LSP IP Allowlists | PUT/DELETE on /lsps/{lspId}/api-ip-allowlist and /ui-ip-allowlist plus enforcement toggle controls per-surface IP restrictions; enforcement applied via LspSurfaceIpAllowlistFilter. | Pass | API and UI allowlist enforcement returned 403 from blocked forwarded IP and cleanup restored enforcement. | System Administrator | Security/IP Allowlist | PDF + code | API | /api/v1/internal/admin/lsps/{lspId}/api-ip-allowlist, /ui-ip-allowlist, /allowlist-enforcement | Phase 3 allowlist probes |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-010 | Create Internal or LSP User | POST /api/v1/internal/admin/users (SYSTEM_ADMIN) creates user with role(s) and optional LSP scope; must_change_password flag set on initial password. | Pass | Created LSP UI user through admin API and login succeeded. | System Administrator | User Admin | PDF + code | API | POST /api/v1/internal/admin/users + /users UI | POST /admin/users; POST /auth/login |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-011 | Update User or Reset Password | PUT /users/{userId} edits status/roles (with last-SYSTEM_ADMIN + self-disable guards). POST /users/{userId}/reset-password mints temporary password and forces change on next login. POST /users/{userId}/revoke-sessions bumps token_version invalidating active JWTs. | Needs Verification | Reset-password and revoke-session subflows passed, but PUT user update/role/status guards were not fully exercised. | System Administrator | User Admin | PDF + code | API | PUT /api/v1/internal/admin/users/{userId}, POST /reset-password, POST /revoke-sessions | POST reset-password; POST revoke-sessions; PUT user still required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-012 | Create API Client | POST /api/v1/internal/admin/api-clients (SYSTEM_ADMIN) creates client tied to LSP; returns client_id and one-time secret. Audit event recorded. | Pass | Created LSP API client and captured one-time secret. | System Administrator | API Clients | PDF + code | API | POST /api/v1/internal/admin/api-clients + /api-clients UI | POST /admin/api-clients |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-013 | Rotate API Client Secret | POST /api-clients/{id}/rotate-secret issues new secret; grace period (default 300s) keeps old secret valid for cutover; rotation audited. | Pass | Secret rotation grace verified: old secret 200 and new secret 200 during grace window. | System Administrator | API Clients | PDF + code | API | POST /api/v1/internal/admin/api-clients/{id}/rotate-secret | POST rotate-secret + POST /auth/token x2 |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-014 | Create or Update Loan Product | PUT /products/{productId} (SYSTEM_ADMIN/PRODUCT_ADMIN) defines product name, min/max principal, min/max tenure, interest rate, processing fee, status. | Pass | Created loan product successfully. | System Administrator | Products | PDF + code | API | PUT /api/v1/internal/admin/products/{productId} + /products UI | POST /admin/products |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-015 | Configure Product–LSP Mappings | PUT /products/{productId}/mappings and POST /product-lsp-mappings/entries enable/disable per-LSP mapping; only enabled+ACTIVE mappings allow origination & appear in LSP catalog. | Pass | Mapped product to LSP successfully; disabled mapping negative also returned 422. | System Administrator | Products | PDF + code | API | /api/v1/internal/admin/products/{productId}/mappings, /product-lsp-mappings/entries | PUT /products/{id}/mappings; product-lsp-mappings/entries |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-016 | LSP API — Create Loan Application | POST /api/v1/lsp/loan-applications (LSP_API_CLIENT) validates payload, dedups borrower by PAN, creates application + document checklist + intake snapshot, transitions to AWAITING_APPROVAL, fires auto-approval engine. | Pass | LSP API created loan application successfully with INITIALIZED status. | LSP API Client | LSP API / Origination | PDF + code | API | POST /api/v1/lsp/loan-applications | POST /api/v1/lsp/loan-applications |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-017 | Operations — Create Loan Application | Loan creation from operations console (BRD/PDF describes API-only today; CLAUDE.md memory ADR 0003 confirms LSP origination is API-only — no internal UI form). Service path exists via LoanApplicationService.createApplication. | Not Applicable | Internal operations UI loan creation remains intentionally out of scope per ADR 0003; LSP API origination is verified in UC-016. | System Administrator / Operations User | Origination | PDF + code | API | Service: LoanApplicationService.createApplication (no UI form) | Design/ADR review |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-018 | Auto-Approval Rule Evaluation | LoanAutoApprovalRuleEngine evaluates 8 rules: PRODUCT_INACTIVE, LSP_INACTIVE, LSP_PRODUCT_MAPPING_INACTIVE, LOAN_AMOUNT_OUT_OF_RANGE, LOAN_TENURE_OUT_OF_RANGE, BORROWER_REQUIRED_FIELDS_MISSING, REQUIRED_DOCUMENTS_NOT_UPLOADED, BORROWER_HAS_OPEN_LOAN. All pass → APPROVED_PENDING_DISBURSAL + loan_account; any fail → REJECTED with rejection_reason_json. | Pass | After all 8 documents uploaded, fresh run verified status APPROVED_PENDING_DISBURSAL and loanAccountId present. | System (engine) | Auto-Approval | PDF + code | API | Service: LoanAutoApprovalRuleEngine.evaluate | Document upload then GET ops detail |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-019 | Upload KYC Documents (LSP) | POST /lsp/loan-applications/{id}/documents (JSON metadata, multipart single, or multipart batch) stores file via DocumentUploadPolicy and marks checklist item SUBMITTED. PDF/JPEG allow-list, max 10 MB (5 MB for PAN/AADHAAR). | Pass | Uploaded all 8 required documents; checklist submitted=8/8. | LSP API Client / LSP_UI_WRITE | Documents | PDF + code | API | POST /api/v1/lsp/loan-applications/{id}/documents{,/batch} | POST /lsp/loan-applications/{id}/documents |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-020 | Download KYC Documents (Operations) | GET /ops/loan-applications/{id}/kyc-documents/{type}/content streams file with Content-Disposition; access recorded in LoanApplicationDocumentAccessAudit. /download-all returns zip. | Needs Verification | Fresh run listed KYC documents, but did not independently stream/download document content and verify access audit write. | System Administrator / Operations User | Documents | PDF + code | API | GET /api/v1/internal/ops/loan-applications/{id}/kyc-documents/... | GET kyc-documents list only; content download still required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-021 | Manual Status Transition | POST /ops/loan-applications/{id}/status-transitions (SYSTEM_ADMIN) advances within state machine when canTransitionTo() allows; emits status-change webhook + audit. | Needs Verification | Auto transitions were verified, but manual status transition endpoint was not independently exercised with an operator action. | System Administrator | Lifecycle | PDF + code | API | POST /api/v1/internal/ops/loan-applications/{id}/status-transitions | GET status-transitions; POST manual transition still required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-022 | Manual Status Override | POST /ops/loan-applications/{id}/manual-status (SYSTEM_ADMIN) bypasses normal transition guards; reason code required (MANUAL_ADMIN_OVERRIDE); fully audited. | Needs Verification | Manual status override endpoint not exercised in fresh run. | System Administrator | Lifecycle | PDF + code | API | POST /api/v1/internal/ops/loan-applications/{id}/manual-status | POST /manual-status required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-023 | Invalidate Loan (Pre-Disbursal) | POST /lsp/loan-applications/{id}/invalid (LSP API or via /my-loans UI by LSP_UI_WRITE) requires Idempotency-Key + reason code (with optional text for OTHER); moves to terminal INVALID + cascades to loan_account; fires status-change webhook. | Needs Verification | Invalidate-after-disbursement negative passed, but pre-disbursal successful invalidation was not independently re-tested. | LSP API Client / LSP_UI_WRITE | Lifecycle | PDF + code | API | POST /api/v1/lsp/loan-applications/{id}/invalid | POST /invalid on eligible pre-disbursal app required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-024 | Submit Repayment Schedule | PUT /lsp/loan-applications/{id}/repayment-schedule validates and stores installment plan; schedule becomes a disbursement prerequisite and basis for payment allocation. | Pass | Generated repayment schedule was available with 12 installments; invalid LSP-provided schedule returned 422. | LSP API Client | Disbursement | PDF + code | API | PUT /api/v1/lsp/loan-applications/{id}/repayment-schedule | GET /repayment-schedule; PUT invalid schedule |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-025 | Disbursement Bank Check | POST /lsp/loan-applications/{id}/disbursement-bank-check validates borrower bank details vs disbursement requirements; mismatch logged in LoanDisbursementBankMismatchLog and surfaced as ops alert. | Pass | Bank-check mismatch returned 422 DISBURSEMENT_VALIDATION_FAILED; matching bank details returned 200. | LSP API Client | Disbursement | PDF + code | API | POST /api/v1/lsp/loan-applications/{id}/disbursement-bank-check | POST /disbursement-bank-check |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-026 | Initiate Disbursement | POST /ops/loan-applications/{id}/disbursement-requests (SYSTEM_ADMIN) triggers LoanDisbursementService → adapter; updates loan account + application status per outcome (DISBURSED, DISBURSEMENT_RETRY). | Pass | Admin disbursement request returned 200 on approved loan. | System Administrator | Disbursement | PDF + code | API | POST /api/v1/internal/ops/loan-applications/{id}/disbursement-requests | POST /disbursement-requests |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-027 | Automated Disbursement Processing | LoanDisbursementWorker scheduled run finds APPROVED_PENDING_DISBURSAL / DISBURSEMENT_RETRY apps with met prerequisites, dispatches via adapter; success→DISBURSED→UNDER_REPAYMENT, retryable→DISBURSEMENT_RETRY (up to configured max), exhaustion→ops alert. | Needs Verification | Manual/mock disbursement paths were verified; scheduled worker pickup was not directly observed. | System (worker) | Disbursement | PDF + code | API | Worker: LoanDisbursementWorker | Worker cadence/log assertion required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-028 | Simulate Disbursement Outcome | POST /ops/loan-applications/{id}/disbursement-requests/mock-outcome applies a chosen MockDisbursementOutcome (SUCCESS/RETRYABLE_FAILURE/PERMANENT_FAILURE); only active when mock adapter enabled. | Pass | Mock disbursement success endpoint returned 200 in local profile. | System Administrator | Disbursement (Mock) | PDF + code | API | POST /api/v1/internal/ops/loan-applications/{id}/disbursement-requests/mock-outcome | POST /disbursement-requests/mock-outcome |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-029 | Record Payment (Internal Operations) | POST /ops/loan-applications/{id}/payments (SYSTEM_ADMIN/OPS_USER) requires Idempotency-Key + targetInstallmentId + exact installment amount + channel (NEFT/RTGS/IMPS); allocates to that installment; advances DISBURSED→UNDER_REPAYMENT on first payment; CLOSED on last installment. | Pass | Internal ops payments loop paid 12 installments; final application and loan account status CLOSED. | System Administrator / Operations User | Servicing | PDF + code | API | POST /api/v1/internal/ops/loan-applications/{id}/payments | POST /payments x12; GET ops detail |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-030 | Record Payment (LSP API) | POST /lsp/loans/{loanId}/payments mirrors ops payment validation (idempotent, full installment amount, channel); same status transitions and webhooks fire. | Needs Verification | LSP API payment endpoint was not independently exercised; ops payment path passed. | LSP API Client | Servicing | PDF + code | API | POST /api/v1/lsp/loans/{loanId}/payments | POST /api/v1/lsp/loans/{loanId}/payments required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-031 | Request Foreclosure Quote | POST /lsp/loans/{loanId}/foreclosure-quote or /ops/.../foreclosure-quotes calculates payoff amount + validity period; quote stored for later execution. | Needs Verification | Fresh foreclosure quote attempts were made after closure and returned 422; eligible-loan quote path not verified. | System Administrator / LSP API Client | Servicing | PDF + code | API | POST /api/v1/lsp/loans/{loanId}/foreclosure-quote, POST /api/v1/internal/ops/loan-applications/{id}/foreclosure-quotes | POST foreclosure quote on eligible loan required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-032 | Execute Foreclosure | POST /lsp/loans/{loanId}/foreclosure-quotes/{quoteId}/execute or ops equivalent applies foreclosure → terminal FORECLOSED; partner notified via webhook. | Needs Verification | Fresh execute attempt lacked a valid quote id after quote failure; execute path not verified. | System Administrator | Servicing | PDF + code | API | POST /api/v1/lsp/loans/{loanId}/foreclosure-quotes/{quoteId}/execute, POST /ops/loan-applications/{id}/foreclosure-quotes/{quoteId}/execute | POST foreclosure execute with valid quote required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-033 | Update Borrower Bank Details | PATCH /lsp/borrowers/{borrowerId}/bank-details and ops equivalent persist bank account, ifsc, holder name; audited in BorrowerBankDetailsUpdateAudit; may trigger borrower.bank.updated webhook. | Needs Verification | Invalid IFSC negative returned 400, but successful borrower bank update/audit was not verified. | System Administrator / LSP API Client | Borrowers | PDF + code | API | PATCH /api/v1/lsp/borrowers/{borrowerId}/bank-details, PATCH /api/v1/internal/admin/borrowers/{borrowerId}/bank-details | PATCH bank-details valid path required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-034 | Search and View Borrowers | GET /borrowers list (with filters) and GET /borrowers/{id} return borrower profile + linked loans + DPD aggregate; aadhaar masked in API responses. | Pass | Borrower 360 returned 200 for fresh borrower. | System Administrator / Operations User | Borrowers | PDF + code | API | GET /api/v1/internal/admin/borrowers, GET /borrowers/{id} + /borrowers UI | GET /admin/borrowers/{id} |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-035 | View Portfolio Dashboard | GET /home/overview returns HomeDashboardSummary: totals (disbursed/active/overdue), applications-by-status, DPD buckets, openAlerts, avg approval TAT (30d), critical disbursements. | Pass | Home overview returned 200 and Playwright loaded primary /home screen without console errors. | System Administrator | Home Dashboard | PDF + code | API | GET /api/v1/internal/home/overview + /home UI | GET /home/overview; Playwright /home |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-036 | Search Loan Applications | GET /ops/loan-applications supports filters (status, LSP, product, source, search, disbursal date range); cursor pagination; sensitive-data toggle masks PII columns. | Pass | Loan applications UI/API filtering passed in Playwright phase. | System Administrator / Operations User | Loan Applications | PDF + code | API | GET /api/v1/internal/ops/loan-applications + /loan-applications UI | GET/list + Playwright filters |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-037 | Portfolio MIS — Preview and Sync Download | GET /reports/portfolio-mis/preview returns first N rows (aadhaar + bank account masked). GET /reports/portfolio-mis (text/csv) streams full report for sync download. Date range + LSP filter. | Pass | MIS preview and synchronous CSV returned 200 with CSV content type. | System Administrator | Reports | PDF + code | API | GET /api/v1/internal/reports/portfolio-mis/preview, /portfolio-mis (CSV) + /reports UI | GET portfolio-mis/preview and portfolio-mis CSV |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-038 | Async MIS Report Generation | POST /reports/portfolio-mis/requests queues report; ReportRequestProcessingWorker generates CSV in storage (R2 or local); GET /reports/requests + /requests/{id}/download retrieve. | Pass | Async MIS request completed and download returned 200 CSV. | System Administrator | Reports | PDF + code | API | POST /api/v1/internal/reports/portfolio-mis/requests, GET /requests, GET /requests/{id}/download | POST report request; poll; download |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-039 | Acknowledge Operations Alert | POST /alerts/{alertId}/acknowledge with optional note (≤500 chars) marks alert ACKNOWLEDGED; visible in /alerts table for team coordination. | Pass | Acknowledged an operations alert with 200; long note/double-ack negatives also handled. | System Administrator / Operations User | Alerts | PDF + code | API | POST /api/v1/internal/alerts/{alertId}/acknowledge + /alerts UI | POST /alerts/{id}/acknowledge |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-040 | Escalate Loan to Administrator | POST /alerts/escalate (OPS_USER) creates OPS_USER_ESCALATION alert tied to loan application; ESCALATE button replaced Approve/Reject in OPS UI (Gap #16). | Needs Verification | Escalation flow was not independently exercised. | Operations User | Alerts | PDF + code | API | POST /api/v1/internal/alerts/escalate + EscalateToAdminDialog UI | POST /alerts/escalate and UI dialog required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-041 | Scheduled Alert Rule Evaluation | AlertRuleSchedulerWorker (5 min cadence) evaluates seven AlertRule entries (stale intake, stuck disbursement, DPD bucket transition, LSP reject spike, etc.); creates/updates OpsAlert deduped via createAlertIfAbsent. | Needs Verification | Alert feed and acknowledge were verified, but scheduled rule evaluation/dedupe was not directly triggered and reconciled. | System (worker) | Alerts | PDF + code | API | Worker: AlertRuleSchedulerWorker, GET /api/v1/internal/alerts/rules | Run scheduler twice with fixture condition required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-042 | Webhook Outbox Dispatch | WebhookOutboxDispatchWorker claims PENDING outbox rows, signs payload, POSTs to subscriber URL; PENDING→DELIVERED on 2xx, →RETRYABLE_FAILURE with backoff, →PERMANENT_FAILURE after max attempts. | Needs Verification | Webhook dispatch endpoint returned 200 with retryable failures, but 2xx delivered path and permanent failure path were not fully verified due localhost SSRF guard. | System (worker) | Webhooks | PDF + code | API | Worker: WebhookOutboxDispatchWorker, POST /api/v1/internal/admin/webhook-outbox/dispatch (manual fire) | Public/non-private webhook receiver required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-043 | Manual Webhook Redrive | POST /webhook-outbox/{id}/redrive (SYSTEM_ADMIN) resets PERMANENT_FAILURE entry to PENDING; redrive audit recorded; subject to max redrive attempts. | Needs Verification | Permission denial for OPS dispatch passed, but SYSTEM_ADMIN redrive of a permanent failure was not verified. | System Administrator | Webhooks | PDF + code | API | POST /api/v1/internal/admin/webhook-outbox/{id}/redrive | POST /webhook-outbox/{id}/redrive required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-044 | Audit Explorer Search | GET /audit-events (SYSTEM_ADMIN) UNION ALL across APPLICATION/INTAKE/DOCUMENT_ACCESS/PRODUCT streams with filter pushdown (actorUsername, lspId, loanApplicationId, borrowerId, productId, since/until). Aadhaar masked in INTAKE detail. offset/limit (cap 500) + optional paginationDetails. | Pass | Audit explorer returned 200. | System Administrator | Audit | PDF + code | API | GET /api/v1/internal/admin/audit-events + /audit UI | GET /admin/audit-events |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-045 | Auth Audit Search | GET /api/v1/internal/ops/auth-audit lists AuthEventAudit (login success/failure, token issuance, password change) with filters. PDF flags 'no dedicated UI'; FE wires via AuditPage timeline streams. | Pass | Auth audit returned 200. | System Administrator | Audit | PDF + code | API | GET /api/v1/internal/ops/auth-audit | GET /ops/auth-audit |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-046 | LSP View Own Loans | GET /lsp/loan-applications + /lsp/loan-applications/{id} + /lsp/loans/{id} return only the authenticated LSP's records via LspTenantContextInterceptor enforcement; /my-loans UI scoped to own tenant. | Pass | LSP view of own loan/application returned 200; cross-tenant LSP access returned 404. | LSP_UI_READ / LSP_UI_WRITE | LSP Self-Service | PDF + code | API | GET /api/v1/lsp/loan-applications, /lsp/loans/{id} + /my-loans UI | GET /lsp/loan-applications/{id}; cross-tenant probe |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-047 | View LSP Product Catalog | GET /api/v1/lsp/products returns only ACTIVE products with an enabled mapping for the authenticated LSP; mapping/product status changes reflected immediately. | Pass | LSP product catalog returned 200 and included mapped product. | LSP API Client / LSP UI User | Products / LSP | PDF + code | API | GET /api/v1/lsp/products | GET /lsp/products |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-048 | Admin Metadata catalog (enums for FE pickers) | GET /api/v1/internal/admin/metadata returns reason codes, status enums, document types, channels for FE dropdown population. Not in PDF. | Pass | Admin metadata returned 200 with role codes. | All internal roles | Admin Metadata | PDF + code | API | GET /api/v1/internal/admin/metadata | GET /admin/metadata |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-049 | LSP Options for admin dropdowns | GET /api/v1/internal/admin/lsp-options returns lightweight LSP list (id+name+status) for filter pickers in ops UIs. Not in PDF. | Needs Verification | Admin LSP options/dropdown endpoint not independently verified in fresh run. | All internal roles | LSP Admin | PDF + code | API | GET /api/v1/internal/admin/lsp-options | GET admin options endpoint required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-050 | Per-application webhook events view (Gap #5) | GET /ops/loan-applications/{id}/webhook-events returns ≤200 outbox rows newest-first for SYSTEM_ADMIN/OPS_USER with status mapped to PENDING/DELIVERED/FAILED/DEAD_LETTERED. Not in PDF. | Pass | Per-loan webhook events endpoint returned 200 in Newman and UI/API count sync passed in Playwright. | System Administrator / Operations User | Webhooks | PDF + code | API | GET /api/v1/internal/ops/loan-applications/{id}/webhook-events | GET /webhook-events; Playwright Webhooks tab |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-051 | Borrower bank details retrieval (LSP) | GET /lsp/borrowers/{borrowerId}/bank-details returns current bank info for the authenticated LSP's borrower; PATCH update covered in UC-033. | Pass | LSP borrower bank details retrieval was used successfully before disbursement-bank-check. | LSP API Client | Borrowers | PDF + code | API | GET /api/v1/lsp/borrowers/{borrowerId}/bank-details | GET /lsp/borrowers/{id}/bank-details |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-052 | Document access audit per application | GET /ops/loan-applications/{id}/document-access-audits returns DOCUMENT_ACCESS audit rows for compliance review; access logged on every download. | Needs Verification | Document-access audit endpoint returned 200, but a fresh content download followed by audit-row assertion was not performed. | System Administrator / Operations User | Audit | PDF + code | API | GET /api/v1/internal/ops/loan-applications/{id}/document-access-audits | GET document content then audit row required |  | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-053 | UI stale state without refresh (added during execution) | Loan detail page reflects API status within 30s or on manual refresh. | Fail | Playwright confirmed known gap: UI detail remained stale after external API payment/status change. | System Administrator | UI Sync | E2E execution | UI | /loan-applications/{id} | Playwright EC-111 | Medium | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-054 | loanAccountId null after DISBURSED (added during execution) | GET ops loan application returns loanAccountId when status is DISBURSED. | Pass | Auto approval detail included loanAccountId before disbursement; disbursed fixture retained loanAccountId. | System Administrator | Lifecycle | E2E execution | API | GET /ops/loan-applications/{id} | GET ops detail | High | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
UC-055 | AlertRuleSchedulerWorker tenant context (added during execution) | Scheduled alert evaluation runs without MissingTenantContextException. | Needs Verification | No MissingTenantContext was not proven by a direct scheduler trigger/log assertion in this run. | System (worker) | Alerts | E2E execution | Backend | AlertRuleSchedulerWorker | Trigger AlertRuleSchedulerWorker and inspect logs/alerts | Critical | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.

## Edge Cases
UC | The use case | Expected behaviour | Pass / Fail | Actual behaviour / Current behaviour | Actor | Module | Source | Test Type | API / Screen | Steps Performed | Severity | Notes
EC-001 | Login with wrong password | POST /auth/login with invalid password → 401 with no user enumeration; AuthEventAudit entry with failure reason BAD_CREDENTIALS. | Pass | Wrong password returned 401. | All humans | Authentication | Code audit | API | POST /api/v1/auth/login | POST /auth/login | High | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-002 | Login with unknown username | POST /auth/login with non-existent user → 401 with identical body/timing as wrong-password to avoid user enumeration. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | All humans | Authentication | Code audit | API | POST /api/v1/auth/login | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-003 | Brute-force lockout (issue #155) | After N consecutive failed logins for same username, account is locked for cooldown window; alert raised; user receives lockout message on next attempt (resolved per PR #196). | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | All humans | Authentication | Code audit | API | POST /api/v1/auth/login | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-004 | Inactive user attempts login | POST /auth/login for status=DISABLED user → 401/403 with disabled-account reason; AuthEventAudit captures. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | All humans | Authentication | Code audit | API | POST /api/v1/auth/login | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-005 | Expired access token | Internal endpoint with expired JWT → 401; FE silently refreshes via /auth/refresh; if refresh also expired, redirect to /login. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | All authenticated | Authentication | Code audit | API | Any /api/v1/internal/* endpoint | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-006 | Tampered JWT (signature mismatch) | Endpoint call with hand-edited JWT (changed sub or role) → 401; no role escalation possible. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Attacker | Authentication | Code audit | API | Any authenticated endpoint | Add targeted API/UI/DB/log probe | Critical | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-007 | Token revoked via session invalidation | After POST /users/{userId}/revoke-sessions or role change, prior access tokens fail with tv-claim mismatch → 401. | Pass | Revoked token reuse → 401 | System Administrator | Authentication | Code audit | API | POST /api/v1/internal/admin/users/{userId}/revoke-sessions | revoke-sessions + GET context | High | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-008 | API client with rotated secret (within grace) | Old secret continues to work for grace window (300s default) after rotation; after expiry → 401. | Pass | Rotate grace old=200 new=200 | LSP API Client | Authentication | Code audit | API | POST /api/v1/auth/token | POST rotate-secret + token x2 | Medium | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-009 | API client used by inactive LSP | Valid client_id+secret on deactivated LSP → 401/403; LspStatusService cascade ensures client disabled. | Pass | Inactive LSP token → 401 | LSP API Client | Authentication | Code audit | API | POST /api/v1/auth/token | POST /auth/token | High | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-010 | IP allowlist violation (LSP API) | API call from IP not in API allowlist (enforcement enabled) → 403 with allowlist-violation reason; OpsAlert fires on repeated violations. | Pass | Token from blocked IP → 403 | LSP API Client | Security/IP Allowlist | Code audit | API | Any /api/v1/lsp/* endpoint | POST /auth/token + X-Forwarded-For | High | Fresh evidence: phase3-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-011 | IP allowlist violation (LSP UI) | /login or any /my-loans request from non-allowlisted IP for LSP UI user → 403. | Pass | LSP UI login blocked IP → 403 | LSP UI User | Security/IP Allowlist | Code audit | API | /login (LSP user), /my-loans | POST /auth/login + X-Forwarded-For | High | Fresh evidence: phase3-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-012 | Cross-tenant LSP access attempt | LSP A's token used to GET /lsp/loan-applications/{id} where id belongs to LSP B → 404 (not 403, to avoid leaking existence). | Pass | LSP B → LSP A application → 404 | LSP API Client | Tenancy / Isolation | Code audit | API | GET /api/v1/lsp/loan-applications/{id} | GET loan-applications/{id} | Critical | Fresh evidence: phase4-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-013 | Role-bypass attempt (LSP_API_CLIENT hitting admin endpoint) | LSP_API_CLIENT JWT used against /api/v1/internal/admin/* → 403 via @PreAuthorize. | Pass | LSP API token on admin route returned 403. | LSP API Client | Authorization | Code audit | API | Any /api/v1/internal/admin/* endpoint | GET /internal/admin/lsps with LSP token | Critical | Fresh evidence: newman-admin-lsp.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617; requests=79, failed assertions=2 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-014 | OPS_USER attempts SYSTEM_ADMIN-only endpoint | OPS_USER calling /audit-events, /lsps, /products write, /api-clients, /reports → 403. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Operations User | Authorization | Code audit | API | Various SYSTEM_ADMIN-only endpoints | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-015 | PRODUCT_ADMIN attempts non-product endpoint | PRODUCT_ADMIN trying /loan-applications/* or /lsps → 403. | Pass | PRODUCT_ADMIN /admin/lsps → 403 | Product Admin | Authorization | Code audit | API | /api/v1/internal/admin/lsps, /loan-applications | GET /admin/lsps | High | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-016 | Last SYSTEM_ADMIN cannot disable self | PUT /users/{userId} disabling last active SYSTEM_ADMIN → 400 with last-admin guard message (Gap #13 guard). | Needs Verification | Skipped for safety in shared DB: Skipped: disabling sole SYSTEM_ADMIN risks local env lockout. | System Administrator | User Admin | Code audit | API | PUT /api/v1/internal/admin/users/{userId} | Manual sandbox only | High | Run in disposable DB with backup admin ¦ Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-017 | Self password reset by admin → forces change on next login | POST /users/{userId}/reset-password sets must_change_password=true and revokes sessions; user must change on next login. | Pass | Reset login passwordChangeRequired=True | System Administrator | User Admin | Code audit | API | POST /api/v1/internal/admin/users/{userId}/reset-password | POST reset-password + login | Medium | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-018 | Auto-rejection: PRODUCT_INACTIVE | POST /lsp/loan-applications with productId whose status=INACTIVE → application created but auto-REJECTED with PRODUCT_INACTIVE in rejection_reason_json. | Pass | Inactive product intake → 422 | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | POST loan-applications | High | Fresh evidence: phase7-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-019 | Auto-rejection: LSP_INACTIVE | Inactive LSP submits application → REJECTED with LSP_INACTIVE (though token issuance already fails at auth layer — UC-007). | Pass | Inactive LSP token → 401 | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | POST /auth/token | High | Fresh evidence: phase7-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-020 | Auto-rejection: LSP_PRODUCT_MAPPING_INACTIVE | Product valid + LSP active, but mapping disabled → REJECTED with LSP_PRODUCT_MAPPING_INACTIVE. | Pass | Disabled mapping intake → 422 | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | POST loan-applications | High | Fresh evidence: phase7-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-021 | Auto-rejection: LOAN_AMOUNT_OUT_OF_RANGE (below min) | loanAmount < product.minPrincipal → REJECTED with LOAN_AMOUNT_OUT_OF_RANGE. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-022 | Auto-rejection: LOAN_AMOUNT_OUT_OF_RANGE (above max) | loanAmount > product.maxPrincipal → REJECTED. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-023 | Auto-rejection: LOAN_TENURE_OUT_OF_RANGE | tenure < minTenureMonths or > maxTenureMonths → REJECTED with LOAN_TENURE_OUT_OF_RANGE. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-024 | Auto-rejection: BORROWER_REQUIRED_FIELDS_MISSING | Missing/blank any of: fullName, pan, mobile, aadharNumber, addressLine1, city, state, zip, monthlyIncome>0, referencePersonName, referencePersonNumber → REJECTED with BORROWER_REQUIRED_FIELDS_MISSING. | Pass | Sparse intake → 400 | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | POST loan-applications | High | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-025 | Auto-rejection: REQUIRED_DOCUMENTS_NOT_UPLOADED | Approval-required documents missing from checklist at AWAITING_APPROVAL → REJECTED with REQUIRED_DOCUMENTS_NOT_UPLOADED. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-026 | Auto-rejection: BORROWER_HAS_OPEN_LOAN | PAN already linked to another open loan across ANY LSP → REJECTED with BORROWER_HAS_OPEN_LOAN (one-open-loan rule). | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Auto-Approval | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | Critical | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-027 | Duplicate intake (idempotency replay) | POST /lsp/loan-applications with same Idempotency-Key + fingerprint → returns first response (200 with same applicationId); fingerprint mismatch → 409. | Pass | Replay idem → 200/200 sameId=True | LSP API Client | Idempotency | Code audit | API | POST /api/v1/lsp/loan-applications | POST loan x2 | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-028 | Invalid payload — missing required field | POST /lsp/loan-applications missing lspLoanId / productId / loanAmount → 400 with validation error array; no DB write. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Validation | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-029 | Invalid PAN format | PAN not matching AAAAA9999A regex → 400 validation error. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Validation | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-030 | Mismatched lspId in payload vs token | Request body's lspId ≠ authenticated LSP → AccessDeniedException (403). | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Tenancy / Isolation | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | Critical | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-031 | Malformed JSON body | Invalid JSON → 400 from Spring HttpMessageNotReadable handler; no stack trace leaked. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Any client | Validation | Code audit | API | Any POST/PUT/PATCH endpoint | Add targeted API/UI/DB/log probe | Low | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-032 | Oversized request body | JSON beyond Spring max-request-size → 413 / 400; documents > policy max → 400 with size violation. | Pass | Oversized body → 413 | Any client | Validation | Code audit | API | POST /lsp/loan-applications/{id}/documents | POST huge JSON | Medium | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-033 | Illegal status transition (REJECTED → anything) | POST /ops/loan-applications/{id}/status-transitions from REJECTED → 400/409 because terminal status cannot transition (canTransitionTo returns false). | Pass | REJECTED→APPROVED → 422 | System Administrator | Lifecycle | Code audit | API | POST /api/v1/internal/ops/loan-applications/{id}/status-transitions | POST transition | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-034 | Illegal status transition (CLOSED → anything) | Same as EC-033 for CLOSED (terminal). | Pass | CLOSED→DISBURSED → 422 | System Administrator | Lifecycle | Code audit | API | POST /status-transitions | POST transition | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-035 | Illegal status transition (FORECLOSED → anything) | FORECLOSED rejects all subsequent transitions. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator | Lifecycle | Code audit | API | POST /status-transitions | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-036 | Illegal status transition (INVALID → anything) | INVALID rejects all transitions; cascaded loan_account stays INVALID-mirrored. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator | Lifecycle | Code audit | API | POST /status-transitions | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-037 | Invalidate after disbursement | POST /lsp/loan-applications/{id}/invalid on DISBURSED/UNDER_REPAYMENT/CLOSED/FORECLOSED → 400 (only PRE_DISBURSAL_STATUSES allowed). | Pass | Invalidate DISBURSED → 422 | LSP API Client / LSP_UI_WRITE | Lifecycle | Code audit | API | POST /api/v1/lsp/loan-applications/{id}/invalid | POST invalid | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-038 | Invalidation idempotency — same key repeated | Second call with identical Idempotency-Key + fingerprint returns first response (200, same applicationId/status); different fingerprint → 409. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Idempotency | Code audit | API | POST /api/v1/lsp/loan-applications/{id}/invalid | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-039 | Manual status transition without required reason | POST /status-transitions with reasonCode-required target but missing reasonCode → 400. | Pass | REJECTED no reasonCode → 422 | System Administrator | Lifecycle | Code audit | API | POST /status-transitions | POST transition | Medium | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-040 | Upload disallowed MIME type | Upload .exe / .bin → 400 from DocumentUploadPolicy; not persisted. | Pass | text/plain → 422 | LSP API Client / LSP_UI_WRITE | Documents | Code audit | API | POST /api/v1/lsp/loan-applications/{id}/documents | POST doc | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-041 | Upload file exceeding size cap | PAN/AADHAAR upload > 5 MB → 400; other docs > 10 MB → 400 (DocumentUploadPolicy per-type caps). | Pass | 11MB upload → 413 | LSP API Client / LSP_UI_WRITE | Documents | Code audit | API | POST .../documents | POST document | Medium | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-042 | Upload document not on checklist | documentType not in LoanApplicationDocumentRequirements for that product → 400. | Pass | Bad documentType → 400 | LSP API Client | Documents | Code audit | API | POST .../documents | POST document | Medium | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-043 | Upload to non-existent application | POST .../documents on random UUID → 404. | Pass | Random app doc → 404 | LSP API Client | Documents | Code audit | API | POST .../documents | POST doc | Low | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-044 | Cross-tenant document download | OPS GET /kyc-documents/{type}/content for app outside scope → 404; download attempt audited. | Pass | LSP B list LSP A docs → 404 | System Administrator / Operations User | Documents | Code audit | API | GET /api/v1/internal/ops/loan-applications/{id}/kyc-documents/{type}/content | GET documents | Critical | Fresh evidence: phase4-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-045 | Download non-existent document type | GET .../kyc-documents/PAN_CARD/content on app with no PAN_CARD uploaded → 404 with checklist-pending reason. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Operations User | Documents | Code audit | API | GET .../kyc-documents/{type}/content | Add targeted API/UI/DB/log probe | Low | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-046 | Disbursement attempted on non-eligible status | POST /disbursement-requests on AWAITING_APPROVAL or REJECTED or INVALID → 400 (only APPROVED_PENDING_DISBURSAL / DISBURSEMENT_RETRY allowed). | Pass | Disburse INITIALIZED → 422 | System Administrator | Disbursement | Code audit | API | POST /api/v1/internal/ops/loan-applications/{id}/disbursement-requests | POST disbursement | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-047 | Disbursement attempted without repayment schedule | Eligible status but no schedule on file → 400 with schedule-missing reason; LoanDisbursementWorker skips and emits OpsAlert. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator / System | Disbursement | Code audit | API | POST /disbursement-requests | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-048 | Disbursement attempted with bank mismatch | Bank check failed earlier or borrower bank holder name fails matcher → disbursement blocked; LoanDisbursementBankMismatchLog row + ops alert. | Pass | mismatch → 422 (DISBURSEMENT_VALIDATION_FAILED); match → 200 | System / System Administrator | Disbursement | Code audit | API | POST /disbursement-requests, worker | POST disbursement-bank-check mismatch vs match | High | Fresh evidence: phase7-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-049 | Disbursement retry exhaustion | After N retryable failures, application stays DISBURSEMENT_RETRY → OpsAlert DISBURSEMENT_RETRY_EXHAUSTED; manual SYSTEM_ADMIN intervention required. | Pass | mock FAILED x5, status=DISBURSEMENT_RETRY | System (worker) | Disbursement | Code audit | API | Worker: LoanDisbursementWorker | POST disbursement + mock-outcome FAILED loop | High | Fresh evidence: phase9-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-050 | Mock disbursement outside test mode | POST /disbursement-requests/mock-outcome in env where mock adapter disabled → 404/400. | Needs Verification | Non-local profile behavior not verified: Local profile exposes mock-outcome → 404. | System Administrator | Disbursement (Mock) | Code audit | API | POST .../mock-outcome | POST mock-outcome | Low | Requires non-local profile to assert 404/403; N/A on local dev. ¦ Fresh evidence: phase3-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-051 | Payment without Idempotency-Key | POST /payments missing Idempotency-Key header → 400 (Gap #17 contract enforces). | Pass | No Idempotency-Key → 400 | System Administrator / Operations User / LSP API Client | Servicing | Code audit | API | POST /api/v1/internal/ops/loan-applications/{id}/payments, POST /api/v1/lsp/loans/{id}/payments | POST payment | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-052 | Payment without targetInstallmentId | POST /payments missing targetInstallmentId → 400. | Pass | no targetInstallmentId → 400 | System Administrator / Operations User / LSP API Client | Servicing | Code audit | API | POST /payments | POST payment | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-053 | Partial installment amount rejected | Amount ≠ installment.due → 400 with BR-13 violation; no payment recorded. | Pass | partial → 422 | Any payer | Servicing | Code audit | API | POST /payments | POST payment | Critical | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-054 | Payment to already-PAID installment | targetInstallmentId already PAID → 400/409 with installment-already-paid reason. | Pass | Double pay → 200/409 | Any payer | Servicing | Code audit | API | POST /payments | POST payment x2 | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-055 | Payment idempotency replay | Same Idempotency-Key + fingerprint → returns prior response; different fingerprint with same key → 409. | Pass | Payment idem replay → 200/200 | Any payer | Idempotency | Code audit | API | POST /payments | POST payment x2 same key | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-056 | Payment with invalid channel | channel not in NEFT/RTGS/IMPS → 400 enum validation. | Pass | bad channel → 400 | Any payer | Servicing | Code audit | API | POST /payments | POST payment | Medium | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-057 | Payment on closed/foreclosed loan | POST /payments on CLOSED or FORECLOSED loan → 400. | Pass | Payment on CLOSED → 422 | Any payer | Servicing | Code audit | API | POST /payments | POST payment | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-058 | Foreclosure quote on non-eligible loan | POST /foreclosure-quote on AWAITING_APPROVAL or REJECTED → 400. | Pass | Foreclosure INITIALIZED → 422 | System Administrator / LSP API Client | Servicing | Code audit | API | POST /api/v1/lsp/loans/{id}/foreclosure-quote | POST foreclosure-quotes | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-059 | Foreclosure execute with expired quote | POST /foreclosure-quotes/{quoteId}/execute on quote past validity → 400/409. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator | Servicing | Code audit | API | POST .../foreclosure-quotes/{quoteId}/execute | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-060 | Foreclosure execute on closed/foreclosed loan | Loan already CLOSED/FORECLOSED → 400. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator | Servicing | Code audit | API | POST .../foreclosure-quotes/{quoteId}/execute | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-061 | Webhook to invalid URL (DNS failure) | Subscriber URL unresolvable → RETRYABLE_FAILURE with attempt counter increment; backoff per WebhookOutboxProperties. | Pass | Subscribe invalid host → 422 | System (worker) | Webhooks | Code audit | API | Worker: WebhookOutboxDispatchWorker | PUT webhook-subscription | Medium | Fresh evidence: phase5-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-062 | Webhook subscriber returns 5xx | HTTP 5xx → RETRYABLE_FAILURE; honor backoff. | Needs Verification | Not fully verified: Subscribe localhost mock blocked by SSRF guard → 422; local SSRF guard blocked localhost subscriber setup. | System (worker) | Webhooks | Code audit | API | Worker: WebhookOutboxDispatchWorker | PUT webhook-subscription | Medium | Use a non-private webhook URL or SSRF test bypass for local E2E. ¦ Fresh evidence: phase5-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-063 | Webhook subscriber returns 4xx (non-retryable) | HTTP 4xx (except 408/429) → PERMANENT_FAILURE; OpsAlert WEBHOOK_DEAD_LETTER raised; available for manual redrive. | Needs Verification | Not fully verified: Subscribe localhost mock blocked by SSRF guard → 422; local SSRF guard blocked localhost subscriber setup. | System (worker) | Webhooks | Code audit | API | Worker: WebhookOutboxDispatchWorker | PUT webhook-subscription | High | Use a non-private webhook URL or SSRF test bypass for local E2E. ¦ Fresh evidence: phase5-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-064 | Webhook redrive without permission | Non-SYSTEM_ADMIN POST /webhook-outbox/{id}/redrive → 403. | Pass | OPS redrive → 403 | Operations User | Webhooks | Code audit | API | POST /api/v1/internal/admin/webhook-outbox/{id}/redrive | POST dispatch | High | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-065 | Webhook signature header missing on payload | Subscriber test should verify X-Bhawana-Signature is present and HMAC matches; absence indicates regression. | Needs Verification | Not verified in LMS API run; webhook HMAC verification is consumer-side and needs receiver-level test. | External LSP webhook consumer | Webhooks | Code audit | API | Webhook payload | N/A for LMS API runner | High | Document in integration tests for webhook consumers. ¦ Fresh evidence: phase5-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-066 | SSRF in webhook URL | Subscription URL pointing to internal hosts (169.254.169.254, localhost) → rejected by SsrfSafeUrlValidator at save time. | Pass | Subscribe SSRF URL → 422 | System Administrator | Security/Webhooks | Code audit | API | PUT /api/v1/internal/admin/lsps/{lspId}/webhook-subscription | PUT webhook-subscription | Critical | Fresh evidence: phase5-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-067 | MIS preview leaks unmasked aadhaar | GET /reports/portfolio-mis/preview MUST mask aadhaar as XXXXXXXX#### and bank_account as XXXX#### per Gap #10; any unmasked → Critical fail. | Pass | Unmasked aadhaar fields: none | System Administrator | Reports / PII | Code audit | API | GET /api/v1/internal/reports/portfolio-mis/preview | GET portfolio-mis/preview | Low | Fresh evidence: phase9-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-068 | MIS CSV download large dataset | Async path: POST /reports/portfolio-mis/requests for year-wide range → request transitions PENDING→PROCESSING→COMPLETED; CSV downloadable. | Needs Verification | Performance gate not verified: Portfolio has 57 loans (<100 required for perf gate). | System Administrator | Reports | Code audit | API | POST /reports/portfolio-mis/requests, GET /requests/{id}/download | GET portfolio-mis CSV | Medium | Seed staging data or enable demo portfolio seed ¦ Fresh evidence: phase9-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-069 | Report download unauthorized user | OPS_USER hitting /reports/* → 403. | Pass | OPS MIS → 403 | Operations User | Reports | Code audit | API | GET /api/v1/internal/reports/* | GET portfolio-mis | High | Fresh evidence: phase2-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-070 | Empty filter range — no data | MIS request with future-only date range → empty CSV with header row only; no 500. | Pass | Empty MIS range → 200 | System Administrator | Reports | Code audit | API | GET /reports/portfolio-mis | GET MIS preview | Low | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-071 | Borrower lookup across tenants (LSP) | LSP A querying borrower belonging only to LSP B → 404 (not 403). | Pass | LSP B → LSP A borrower → 404 | LSP API Client | Tenancy | Code audit | API | GET /api/v1/lsp/borrowers/{id}/bank-details | GET bank-details | Critical | Fresh evidence: phase4-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-072 | Borrower bank update with invalid IFSC | PATCH bank-details with malformed IFSC → 400. | Pass | Bad IFSC → 400 | LSP API Client / SYSTEM_ADMIN | Borrowers / Validation | Code audit | API | PATCH /api/v1/lsp/borrowers/{id}/bank-details | PATCH bank-details | Medium | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-073 | Borrower aadhaar masked on read | GET /admin/borrowers/{id} returns aadhaar masked (XXXXXXXX####); raw aadhaar never returned in any API. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Internal roles | PII Masking | Code audit | API | GET /api/v1/internal/admin/borrowers/{id} | Add targeted API/UI/DB/log probe | Critical | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-074 | Rate limit on /auth/login per IP+username | Excess requests in window → 429 with Retry-After; RateLimitFilter emits ops alert on breach (Follow-up #2). | Pass | Login burst codes → [429, 429, 429, 429, 429, 429, 429, 429] | Any client | Rate Limiting | Code audit | API | POST /api/v1/auth/login | POST /auth/login x8 | High | Fresh evidence: phase6-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-075 | Rate limit on /auth/token per client_id | Excess token issuance → 429. | Pass | Token burst codes → [401, 401, 401, 401, 401, 429, 429, 429] | LSP API Client | Rate Limiting | Code audit | API | POST /api/v1/auth/token | POST /auth/token x8 | Medium | Fresh evidence: phase6-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-076 | Rate limit on /lsp/loan-applications per LSP | Burst of intake calls beyond bucket → 429 with Retry-After. | Fail | Rate-limit burst reached 429 but also produced backend 500s: LSP write burst → [500, 500, 500, 200, 500, 200, 500, 429, 429, 429, 429, 429]. Expected graceful 429 only. | LSP API Client | Rate Limiting | Code audit | API | POST /api/v1/lsp/loan-applications | POST loan-applications x12 | Medium | Production risk: LSP write burst should not surface 500 responses under rate limiting. ¦ Fresh evidence: phase6-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-077 | Acknowledge non-existent alert | POST /alerts/{random-uuid}/acknowledge → 404. | Pass | Random alert → 404 | Operations User | Alerts | Code audit | API | POST /api/v1/internal/alerts/{id}/acknowledge | POST acknowledge | Low | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-078 | Acknowledge note over 500 chars | Body.note length > 500 → 400 (Gap #15 validation). | Pass | Long note → 400 | Operations User | Alerts / Validation | Code audit | API | POST /alerts/{id}/acknowledge | POST acknowledge | Low | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-079 | Acknowledge already-acknowledged alert | Second ack on same alert → idempotent (returns updated ack metadata; no error). | Pass | Double ack → 409 | Operations User | Alerts | Code audit | API | POST /alerts/{id}/acknowledge | POST acknowledge x2 | Low | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-080 | Alert dedupe (same condition, same loan) | AlertRuleSchedulerWorker re-evaluates and finds same condition → createAlertIfAbsent returns existing open alert (no duplicate row). | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System (worker) | Alerts | Code audit | API | Worker: AlertRuleSchedulerWorker | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-081 | LSP_UI_WRITE attempts /loan-applications (internal route) | RequireInternal guard blocks → redirected to /my-loans. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP UI User | Frontend Guards | Code audit | UI | /loan-applications UI | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-082 | OPS_USER navigates to /reports | RequireRole guard blocks (SYSTEM_ADMIN_ONLY); shows PermissionDeniedState. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Operations User | Frontend Guards | Code audit | UI | /reports UI | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-083 | Browser refresh on detail page preserves session | F5 on /loan-applications/{id} → silent refresh + same view; no auth bounce. | Pass | Browser refresh preserves session on loan detail — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Internal user | Frontend / Session | Code audit | UI | /loan-applications/{id} | Playwright edge-coverage-phase8 | Medium | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-084 | 401 from backend mid-session | FE intercepts 401 → triggers /auth/refresh → retries; if both fail → redirect to /login with return URL. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Internal user | Frontend / Session | Code audit | UI | Any UI page | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-085 | Console errors on screen load | Each major screen loads without uncaught errors / unhandled promise rejections in browser console. | Pass | No console errors on primary screens — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Internal user | Frontend | Code audit | UI | All UI pages | Playwright edge-coverage-phase8 | Medium | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-086 | Failed network request surfaces ErrorState | API 5xx → ErrorState component with retry CTA; not a blank screen. | Pass | Failed network shows ErrorState — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Internal user | Frontend | Code audit | UI | All data-fetching pages | Playwright edge-coverage-phase8 | Medium | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-087 | Empty list states | /loan-applications, /borrowers, /alerts, /reports with no rows → EmptyState component (not bare table). | Pass | Empty list states — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Internal user | Frontend / UX | Code audit | UI | All list pages | Playwright edge-coverage-phase8 | Low | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-088 | Pagination boundaries | Hit first/last page; ensure prev/next disabled correctly; page count consistent with total when paginationDetails=true. | Pass | Pagination boundaries on audit — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Internal user | Frontend / List | Code audit | UI + API | /loan-applications, /borrowers, /audit, etc. | Playwright edge-coverage-phase8 | Medium | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-089 | Filter combinations on /loan-applications | Status + LSP + date range simultaneously → server query honors all; result count reconciles with cleared-filter baseline. | Pass | Filter combinations on loan applications — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Operations User | Frontend / Filtering | Code audit | UI + API | /loan-applications | Playwright edge-coverage-phase8 | Medium | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-090 | Sensitive-data toggle | Toggling reveals masked columns; click is audited; refresh respects last toggle state (or resets, depending on spec). | Pass | Sensitive-data toggle — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Operations User | Frontend / PII | Code audit | UI | /loan-applications | Playwright edge-coverage-phase8 | High | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-091 | Audit search with since > until | GET /audit-events?since=X&until=Y where X>Y → 400. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator | Audit / Validation | Code audit | API | GET /api/v1/internal/admin/audit-events | Add targeted API/UI/DB/log probe | Low | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-092 | Audit limit clamping | limit=1000 → clamped to 500; limit=0/-1 → reset to default 100. | Pass | limit=99999 → 200 | System Administrator | Audit | Code audit | API | GET /api/v1/internal/admin/audit-events | GET audit-events | Low | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-093 | Audit unknown stream value | streams=BOGUS → 400. | Pass | Bad streams → 400 | System Administrator | Audit / Validation | Code audit | API | GET /api/v1/internal/admin/audit-events | GET audit-events | Low | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-094 | Audit INTAKE detail masks aadhaar in payload | Even when intake JSON contained raw aadhaar, response detail masks XXXXXXXX####. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator | Audit / PII | Code audit | API | GET /api/v1/internal/admin/audit-events | Add targeted API/UI/DB/log probe | Critical | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-095 | Document access logged on every download | Each GET .../kyc-documents/{type}/content writes a LoanApplicationDocumentAccessAudit row visible in Audit Explorer. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Operations User | Audit / Compliance | Code audit | API | GET .../kyc-documents/{type}/content | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-096 | Status displayed in UI matches DB | After manual override or auto-rejection, /loan-applications list + detail page reflect new status without manual refresh (react-query invalidate). | Pass | UI status matches API — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Internal user | Consistency | Code audit | UI + DB | /loan-applications/{id} | Playwright edge-coverage-phase8 | Medium | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-097 | Webhook event count in detail matches outbox | /loan-applications/{id} Webhooks tab count matches GET .../webhook-events length (cap 200). | Pass | Webhook tab count matches API — app=ee3e0d98-24f6-4c67-8571-572ca8466a20 (fixture ok (DISBURSED)) | Operations User | Consistency | Code audit | API | /loan-applications/{id} | Playwright edge-coverage-phase8 | Medium | Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-098 | First-payment transition disbursed→under_repayment | Recording first installment payment on DISBURSED loan flips status to UNDER_REPAYMENT immediately; subsequent payments stay UNDER_REPAYMENT. | Pass | After 1 pay status=UNDER_REPAYMENT | Operations User | Servicing / State Machine | Code audit | API | POST /payments | GET ops detail | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-099 | Last-installment transition under_repayment→closed | Final installment paid → loan closes (CLOSED) and fully-repaid webhook queued. | Pass | After 12 pay status=CLOSED | Operations User | Servicing / State Machine | Code audit | API | POST /payments | GET ops detail | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-100 | Rejection reason persisted in transition row | Auto-rejection at AWAITING_APPROVAL writes failed RuleCode array into loan_application_status_transition.rejection_reason_json (Gap #11). | Pass | REJECTED transitions=1 structuredReason=True | System (engine) | Auto-Approval / Audit | Code audit | API | DB: loan_application_status_transition.rejection_reason_json | GET status-transitions | Medium | Fresh evidence: phase7-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-101 | PAN dedup links to existing borrower | Second LSP submits app for same PAN → borrower row reused (no duplicate); cross-tenant access controlled. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Borrowers / Dedup | Code audit | API | POST /api/v1/lsp/loan-applications | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-102 | Local backend 401 loop regression (#89 memory) | Authenticated request to admin endpoint with valid JWT should succeed in prod-like profile; if filter chain runs before MVC interceptor sets admin scope (per memory), every call 401s. | Pass | Admin endpoints OK → [200, 200, 200] | System Administrator | Tenancy / Filters | Code audit | API | Any /api/v1/internal/admin/* on live backend | GET internal/admin/* after login | Critical | ADR 0005 tenant scope — no 401 loop ¦ Fresh evidence: phase9-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-103 | Processing fee deduction at disbursement (ADR 0004) | Disbursed amount = principal - processing_fee per product config; loan_account.disbursed_amount + audit reflect deduction. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System | Disbursement / Product | Code audit | API | POST /disbursement-requests, LoanDisbursementService | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-104 | Loan account creation only on approval | loan_account row created exclusively when application transitions to APPROVED_PENDING_DISBURSAL; never before; INVALID/REJECTED apps have no loan_account. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System | Origination | Code audit | API | DB: loan_account | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-105 | Webhook ordering per aggregate | Events for one loan are delivered in created_at order; out-of-order subscriber receives → spec/backend should preserve sequence. | Needs Verification | Weak evidence: Webhook events monotonic by createdAt (0 rows); zero-row ordering does not prove per-aggregate ordering. | External LSP webhook consumer | Webhooks | Code audit | API | WebhookOutboxDispatchWorker | GET webhook-events | Medium | Fresh evidence: phase5-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-106 | Bank holder-name fuzzy match | BankAccountHolderNameMatcher handles minor case/space/initials variations; gross mismatch → mismatch logged. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System | Disbursement / Validation | Code audit | API | BankAccountHolderNameMatcher | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-107 | Schedule submission validation | PUT /repayment-schedule with sum of installments ≠ principal+interest → 400 with ScheduleViolationType detail. | Pass | LSP_PROVIDED bad-sum schedule → 422 (REPAYMENT_SCHEDULE_INVALID) | LSP API Client | Disbursement / Validation | Code audit | API | PUT /api/v1/lsp/loan-applications/{id}/repayment-schedule | PUT repayment-schedule mode=LSP_PROVIDED invalid sum | High | Fresh evidence: phase7-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-108 | Schedule update after disbursement blocked | Re-submitting schedule for DISBURSED loan → 400 (schedule locked post-disbursal). | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | LSP API Client | Servicing | Code audit | API | PUT /repayment-schedule | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-109 | Concurrent disbursement attempts | Two simultaneous disbursement requests for same loan → only one succeeds (DB row lock / status precondition); second sees 409 / no-op. | Needs Verification | Partial evidence: Concurrent disburse → [200, 200]; both calls returned acceptable 2xx, but side-effect count/audit uniqueness was not verified. | System Administrator / System (worker) | Disbursement / Concurrency | Code audit | API | POST /disbursement-requests + worker race | Parallel POST | High | Fresh evidence: phase1-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-110 | Audit explorer correlationId trace | Given a correlationId, FE post-filter (and future BE filter) returns full cross-domain timeline of that operation. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System Administrator | Audit | Code audit | API | GET /api/v1/internal/admin/audit-events | Add targeted API/UI/DB/log probe | Medium | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-111 | UI does not poll loan status after external API changes (added during execution) | Admin UI detail page auto-refreshes or shows stale-data indicator when loan status changes via API. | Fail | Playwright confirmed known gap: after API status/payment change, UI detail remained stale for at least 10s instead of auto-refreshing or showing stale-data state. | System Administrator | UI Sync | E2E execution | UI | /loan-applications/{id} | Playwright edge-coverage-phase8 | Medium | Spec title: EC-111 UI stays stale after API status change (known gap). ¦ Fresh evidence: phase8-results.json in D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617 ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-112 | Bank account number masked on read (admin/MIS/audit/UI) | GET borrowers/{id}, MIS report, and audit must mask bankAccountNumber as XXXX#### (Gap #10); raw account never returned. | Not Applicable | Bank-account masking requirement was previously waived by product; not retested as a required control in this run. Aadhaar masking remains covered separately. | Internal roles | PII Masking | Independent E2E (new) | API + UI | GET /admin/borrowers/{id}; scan MIS CSV + audit payload; verify UI /borrowers/{id} Banking section | Policy/design review | Low | Revisit if bank account becomes regulated PII for internal roles. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-113 | Full-body PII scanner across borrower/report/audit responses | No raw 12-digit aadhaar AND no raw full bank account number in ANY borrower/report/audit response body. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | Internal roles | PII Masking | Independent E2E (new) | API | Regex full JSON/CSV bodies for 12-digit (aadhaar) and 9-18 digit (account) patterns | Add targeted API/UI/DB/log probe | Low | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-114 | DPD / delinquency bucketing on overdue installments | An installment past its due date increments days-past-due and moves the loan into the correct DPD bucket on dashboard + borrower aggregate + MIS. | Needs Verification | No fresh direct verification evidence in the 2026-06-17 independent run; previous result was not reused. | System | Servicing / Risk | Independent E2E (new) | API | Would require back-dating an installment or a business-clock override | Add targeted API/UI/DB/log probe | High | Downgraded from prior matrix status pending independent verification. ¦ Fresh evidence: manual reconciliation ¦ Independent Codex review 2026-06-17; prior Cursor/Claude claims not reused as evidence.
EC-115 | Aggregate actuator health reports DOWN while app is usable | GET /actuator/health should return 200 UP when readiness and business APIs are healthy, or expose precise component failure for ops. | Fail | Fresh check: /actuator/health returned 503 {status:DOWN}; /actuator/health/readiness and /auth/login returned 200. | Operations / SRE | Health / Observability | Independent gap analysis | API | GET /actuator/health | Invoke-WebRequest health/readiness/login | High | Production readiness bug: load balancers/monitors using aggregate health will mark service down.
EC-116 | Refresh-token rotation and replay protection | Refresh endpoint rotates or safely renews refresh token; replay of old refresh token fails; logout invalidates refresh token. | Needs Verification | Missing from fresh coverage; UC-003 only verified logout 204. | All users | Authentication | Gap analysis | API | POST /api/v1/auth/refresh | Add refresh/replay/logout sequence | High | Security-sensitive session lifecycle gap.
EC-117 | LSP deactivation kill-chain cascade | Deactivating an LSP disables API clients, blocks LSP UI/API access, preserves audit trail, and reactivation restores only intended access. | Needs Verification | Only inactive-token denial was tested; full cascade not verified. | System Administrator / LSP | Tenant Admin / Security | Gap analysis | API + UI | PUT /admin/lsps/{id}/status | Deactivate active fixture then attempt API/UI access | Critical | Covers UC-007 production gap.
EC-118 | API client disable and one-time secret reveal | Disabled API client cannot obtain tokens; newly created secret is returned once and never exposed on list/detail. | Needs Verification | Create/rotate passed, but disable and secret non-reveal were not tested. | System Administrator | API Clients / Secrets | Gap analysis | API + UI | /admin/api-clients | Create, list, disable, token exchange, UI secret reveal | High | Security-sensitive client credential lifecycle.
EC-119 | Manual override audit completeness | Manual override requires reason, records actor, timestamp, old/new status, reason code, note, IP, and correlationId. | Needs Verification | Manual override endpoint was not exercised. | System Administrator | Lifecycle / Audit | Gap analysis | API + DB/API audit | POST /manual-status + GET audit-events | Override fixture and inspect audit stream | Critical | Covers UC-022 production gap.
EC-120 | Document ZIP download and per-file audit | Download-all ZIP contains only requested tenant documents and creates document access audit entries for each file. | Needs Verification | Fresh run did not stream content or ZIP. | Operations User | Documents / Audit | Gap analysis | API + DB/API audit | GET /kyc-documents/download-all | Download ZIP, inspect names/counts, check audits | High | Document data leakage and compliance gap.
EC-121 | Document upload filename/path traversal and content sniffing | Filenames with path traversal/control chars are sanitized; file content is validated beyond extension/MIME spoofing. | Needs Verification | MIME and size negatives passed; filename/content-sniffing not covered. | LSP API Client | Documents / Security | Gap analysis | API | POST /documents | Upload spoofed PDF/name payloads | High | Security-sensitive upload hardening.
EC-122 | MIS numeric reconciliation against source rows | MIS totals and row values reconcile to loan_account/payment/schedule source data for selected LSP/date filters. | Needs Verification | MIS endpoints returned 200; numeric reconciliation was not performed. | System Administrator | Reports / MIS Accuracy | Gap analysis | API + DB/API source | GET /reports/portfolio-mis | Compare CSV totals to source API/DB query | High | Reporting correctness gap.
EC-123 | Webhook 2xx/4xx/5xx delivery using public receiver | 2xx marks DELIVERED, 5xx marks RETRYABLE_FAILURE with backoff, 4xx marks PERMANENT_FAILURE; delivery attempts are audited. | Needs Verification | Local receiver was blocked by SSRF guard; Newman dispatch only showed retryable failures. | External webhook consumer | Webhooks | Gap analysis | API + external receiver | PUT webhook-subscription + dispatch | Use public controlled receiver and inspect outbox/attempts | High | Completes EC-062/063 and UC-042 gaps.
EC-124 | Webhook HMAC signature verification by consumer fixture | Consumer can verify signature header over exact payload; tampered payload/signature fails. | Needs Verification | LMS emits payloads, but consumer-side verification was not tested. | External webhook consumer | Webhooks / Security | Gap analysis | Integration | Webhook receiver | Capture payload and validate HMAC | High | Security-sensitive integration gap.
EC-125 | Concurrent disbursement side-effect uniqueness | Parallel disbursement requests create at most one effective disbursement/outcome and one adapter command for the loan. | Needs Verification | Fresh status codes were [200, 200]; side-effect uniqueness was not verified. | System Administrator / Worker | Disbursement / Concurrency | Gap analysis | API + DB/API audit | POST /disbursement-requests in parallel | Inspect request logs/outcome audits/loan account | Critical | Clarifies EC-109 duplicate-action risk.
EC-126 | Idempotency-key conflict with different payload | Reusing an Idempotency-Key with a different request fingerprint returns 409/422 and does not create a second side effect. | Needs Verification | Same-payload replay passed; fingerprint conflict not tested. | LSP API Client / Operations | Idempotency / Security | Gap analysis | API | POST idempotent endpoints | Same key with changed body | High | Prevents accidental/malicious duplicate actions.
EC-127 | Date/timezone boundaries for MIS, DPD, and payments | Boundary dates around midnight/timezone and inclusive date filters are handled consistently for MIS, DPD, and payment posting. | Needs Verification | No boundary-date/timezone fixture was exercised. | System | Reporting / Servicing | Gap analysis | API + DB/API source | MIS, payments, DPD endpoints | Create boundary-date fixtures and reconcile | Medium | Important for production finance/reporting correctness.
EC-128 | Full role-route UI RBAC matrix | Each role sees only allowed navigation and blocked pages render permission denial without data leakage. | Needs Verification | Admin UI passed; OPS/LSP/PRODUCT route matrix not fully covered. | All UI roles | Frontend RBAC | Gap analysis | UI + API | All protected routes | Playwright per-role navigation matrix | High | Completes RBAC/security-sensitive UI coverage.
EC-129 | Audit correlationId end-to-end trace | A single correlationId can retrieve all related auth/API/domain/audit events without raw PII leakage. | Needs Verification | Audit list passed, but correlationId trace was not verified. | System Administrator / Auditor | Audit / Observability | Gap analysis | API + logs | GET /audit-events?correlationId= | Execute request with X-Correlation-Id and query audit/logs | Medium | Operational debugging and compliance gap.
EC-130 | Full PII scanner across borrower/report/audit/document metadata | No raw Aadhaar or other disallowed PII appears in borrower, report, audit, webhook, document metadata, or UI responses. | Needs Verification | MIS Aadhaar scanner passed; full surface scanner not run. | Internal roles / LSP | PII / Security | Gap analysis | API + UI | Borrower/report/audit/webhook/document surfaces | Regex scanner across response bodies and UI text | Critical | Extends EC-067/073/094/113.

## Review Summary
Independent E2E Matrix Review | 2026-06-17
Evidence directory | D:\Desktop-New\Folders\LMS\.e2e-runs\codex-20260617
Workbook backup | D:\Desktop-New\Folders\LMS\e2e-test-matrix.backup-before-codex-20260617-103547.xlsx
API execution mode | Local Newman + direct HTTP phase probes; Postman MCP unavailable (401 Invalid API Key) and user instructed to proceed without it.
Newman result | 79 requests; 2 failed assertions from /actuator/health 503; 2 broken collection assertions on expected 404s.
Phase probes | 74 case results: 68 pass, 6 needs verification before reconciliation; UI Playwright 10/10 executed.
Sheet | Pass | Fail | Needs Verification | Not Applicable | Total
Use Cases | 34 | 1 | 19 | 1 | 55
Edge Cases | 65 | 3 | 61 | 1 | 130
Key Bugs / Risks | Evidence
Aggregate health is DOWN | GET /actuator/health returns 503 while readiness/login are 200 (EC-115).
UI stale after external API change | Playwright EC-111 confirms stale detail page; UC-053/EC-111 marked Fail.
Rate-limit burst leaks 500s | EC-076 returned 500s before 429 under LSP write burst.
Webhook delivery matrix incomplete | Local SSRF guard blocked localhost receiver; public controlled receiver needed.
Many previous passes downgraded | Rows without fresh evidence are marked Needs Verification instead of reusing prior claims.

## Gap Analysis
ID | Gap / Missing test | Status | Severity | Production-readiness note
EC-115 | Aggregate actuator health reports DOWN while app is usable | Fail | High | Production readiness bug: load balancers/monitors using aggregate health will mark service down.
EC-116 | Refresh-token rotation and replay protection | Needs Verification | High | Security-sensitive session lifecycle gap.
EC-117 | LSP deactivation kill-chain cascade | Needs Verification | Critical | Covers UC-007 production gap.
EC-118 | API client disable and one-time secret reveal | Needs Verification | High | Security-sensitive client credential lifecycle.
EC-119 | Manual override audit completeness | Needs Verification | Critical | Covers UC-022 production gap.
EC-120 | Document ZIP download and per-file audit | Needs Verification | High | Document data leakage and compliance gap.
EC-121 | Document upload filename/path traversal and content sniffing | Needs Verification | High | Security-sensitive upload hardening.
EC-122 | MIS numeric reconciliation against source rows | Needs Verification | High | Reporting correctness gap.
EC-123 | Webhook 2xx/4xx/5xx delivery using public receiver | Needs Verification | High | Completes EC-062/063 and UC-042 gaps.
EC-124 | Webhook HMAC signature verification by consumer fixture | Needs Verification | High | Security-sensitive integration gap.
EC-125 | Concurrent disbursement side-effect uniqueness | Needs Verification | Critical | Clarifies EC-109 duplicate-action risk.
EC-126 | Idempotency-key conflict with different payload | Needs Verification | High | Prevents accidental/malicious duplicate actions.
EC-127 | Date/timezone boundaries for MIS, DPD, and payments | Needs Verification | Medium | Important for production finance/reporting correctness.
EC-128 | Full role-route UI RBAC matrix | Needs Verification | High | Completes RBAC/security-sensitive UI coverage.
EC-129 | Audit correlationId end-to-end trace | Needs Verification | Medium | Operational debugging and compliance gap.
EC-130 | Full PII scanner across borrower/report/audit/document metadata | Needs Verification | Critical | Extends EC-067/073/094/113.
Existing rows needing verification | See Use Cases / Edge Cases rows marked Needs Verification | Needs Verification | Mixed | These were not independently proven in the 2026-06-17 fresh run.