## Slide 1
LMS Platform Decision
Build vs buy, governance, operating model, infrastructure, and next-step decision points
Decision focus
Move from a working prototype discussion to an executive path: prove, buy, or build with clear ownership.
Current process
Build option
Buy option
Governance
Prepared for leadership discussion | June 2026

## Slide 2
Current Process: Email Validation and LSP Disbursement
Useful as a control layer, but not the target scalable LMS platform
Bhawana Capital | LMS platform decision
02
1
LSP sends email / data
Input arrives through current LSP channel.
2
GCP script validates
Automated script checks submitted email data.
3
Approval email returns
Approval response is sent back to the LSP.
4
LSP disburses
Disbursement remains outside the platform.
5
PostgreSQL stores approval
Approval record is kept for reference/control.
Current facts
Validation is a GCP script, not a managed platform.
Approvals are returned to the LSP by email.
Only approval evidence is a PostgreSQL record.
Money moves on the LSP's own channel.
What works today
Low-cost way to prove the control concept.
Quick to change while the process is still evolving.
Keeps the current LSP disbursement flow running.
Produces basic approval evidence.
Key risks
Weak control over money flow — disbursement sits outside the platform.
Audit exposure: limited logging, access, and segregation of duties.
Email is not a defensible system of record.
Risk and manual effort grow with every new LSP.
Executive takeaway: keep this as prototype learning, not as the long-term scalable platform.

## Slide 3
Decision to Make: Build vs Buy
The executive decision is not just technology; it is ownership, control, adoption, and auditability
Bhawana Capital | LMS platform decision
03
Option A: Build
Cost
Higher upfront build effort; no recurring licence fees.
Team
Needs dedicated engineering, SDLC, and support capacity.
Governance
Full control of audit model, security, and data path.
Time to Market
Slower: infrastructure, build, and hardening take months.
Option B: Buy
Cost
Lower build effort; recurring licence and change fees.
Team
Vendor-led; less in-house build, but vendor management.
Governance
Shared or limited control; relies on vendor audit/exports.
Time to Market
Faster: mature features sooner, after due diligence.
Decision lens: choose the path that gives LSPs a reason to move, keeps controls auditable, and has clear ownership.

## Slide 4
Prototype Implemented: What It Means
Informative prototype, not production platform
Bhawana Capital | LMS platform decision
04
What exists
A working concept for validation, approval, data capture, and basic workflow.
Useful for learning and vendor comparison.
What does not exist
No production deployment.
No Azure India subscription or production infrastructure.
No proven HA, DR, monitoring, support model, or security certification.
Manual interactions
People still review exceptions, approve decisions, manage partner issues, and own follow-up.
The platform should make these steps auditable.
1
Prototype
2
MVP
3
Pilot
4
Scale
Current state sits at the first point: useful evidence, but not ready for external production use.

## Slide 5
Governance and Operational Model for Option A)
The platform should make compliance easier, not add undocumented manual work
Bhawana Capital | LMS platform decision
05
Area
Platform control
Owner
Manual interaction
Audit evidence
Immutable logs for approvals, status changes, downloads, and exceptions.
Platform + Ops
Ops reviews exception trail.
Security standards
Group SDLC, secure coding, dependency checks, and change approvals.
IT Security + Engineering
Security signs off gates.
Change requests
Formal intake, impact analysis, approval, test evidence, release note.
Internal team in India
Ownership in the team
Access management
Entra ID, role-based access, joiner/mover/leaver process.
Ops
Access owner reviews.
Operations
Runbooks, on-call, incidents, SLAs, partner support queue.
Internal team in India + Platform
Ownership in the team + 24/7 On call support of MITL Platform
Development
Analysis, Development, Testing, Support
Internal team in India
People ownership remains explicit.
Re-use strong governance principles of the group and build ownership for the solution in India – scale up to team of 4 IT People

## Slide 6
Security and Access Model
Use group standards and bank IT Security support from the start
Bhawana Capital | LMS platform decision
06
Identity
Entra ID for users and groups.
Role-based access by function.
Joiner/mover/leaver process.
Audit and evidence
Every approval, exception, data change, and access event should produce searchable audit evidence.
Group security
Bank / group IT Security supports standards, review gates, access model, and production readiness.
Control
Build path
Buy path
Access
Bhawana defines roles and Entra integration.
Vendor must support SSO/RBAC requirements.
Audit
Native platform logs and reporting evidence.
Vendor audit export must be tested.
Security review
Code and infra reviewed internally.
Vendor audit, penetration test, and contract review.

## Slide 7
Current Platform Architecture
Current platform modules, connections, data stores, integrations, and what the platform provides today
Bhawana Capital | LMS platform decision
07

## Slide 8
Infrastructure Direction and Indicative Cost
Start an Azure India subscription only after the decision path is clear
Bhawana Capital | LMS platform decision
08
Initial cloud choice
Azure India subscription for data residency and group-aligned operations.
Indicative run cost
Planning estimate: about EUR 3K per month for a controlled non-large-scale production footprint.
Cost caveat
Actual cost depends on HA, DR, logs retention, data volume, Databricks integration, and vendor contracts.
Infra area
Likely components
Decision needed
Application
App Service / AKS, gateway, monitoring
Build vs vendor deployment model
Data
PostgreSQL, storage, backup, retention
RPO/RTO and data residency
Integration
Databricks DWH, email, LSP channels
Interface ownership and support

## Slide 9
Buy Option: Assessment Required
A vendor decision needs months of diligence, not a demo-only comparison
Bhawana Capital | LMS platform decision
09
Assessment area
What to verify
Owner
Outcome
Functional fit
Origination, approval, audit, reporting, exceptions.
Product + Ops
Fit-gap matrix
Security audit
SSO, RBAC, logs, encryption, vulnerability posture.
IT Security
Security sign-off
Integration
LSP channels, email, PG/DWH/Databricks, APIs.
Engineering
Integration plan
Operations
Support model, SLAs, incident process, release process.
Support + Vendor
RACI
Commercials
License, implementation, change costs, exit rights.
Finance + Legal
TCO and contract
Data governance
Ownership, retention, exports, residency, audit access.
Governance
Control evidence
Key question: who manages what after go-live? Vendor capability does not remove Bhawana ownership of controls, approvals, data, and LSP experience.

## Slide 10
Buy Option: Indicative Vendor Cost
Two live proposals, shown at ~€100M annual scale, first three LSPs, before tax
Bhawana Capital | LMS platform decision
10
Indicative, pre-tax at ~€100M scale: vendor cost scales with disbursement and AUM; Build cost is mostly infra plus an internal team.
Cost element | Vendor A | Vendor B (current) | Build (in-house)
One-time setup | ₹7,500,000 / €69,139 | ₹0 today | Build effort (TBD)
Fixed yearly cost | ₹1,000,000 / €9,219 (AMF) | Floor ₹400,000 / €3,636/mo | Infra ₹3,900,000 / €36,000
Usage fee - based on | 0.20% of disbursement | Tiered % of AUM | None
Usage fee at ~€100M | ₹21,700,000 / €200,000 | ₹28,400,000 / €257,727 | n/a
Year-1 known cost | ₹30,200,000 / €278,358 | ₹28,400,000 / €257,727 | ₹3,900,000 / €36,000 + team
Lock-in / exit | None stated | 36 months | Full control

## Slide 11
Build Option: Gated Roadmap
The current prototype is the starting evidence, not the production end state
Bhawana Capital | LMS platform decision
11
1
0-1 month
Decision and scope
Confirm owner, target process, LSP value case.
2
1-3 months
MVP hardening
Azure, Entra ID, audit, GitHub CI/CD, SDLC.
3
3-5 months
Pilot
One or two LSPs, manual exception flow, reporting.
4
5-8 months
Scale readiness
Monitoring, DR, performance, Databricks DWH.
Hard gate
No production LSP migration until ownership, security, audit, infra, and manual exception operations are proven.
LSP value proof
Pilot must prove the platform is easier for LSPs than email and manual follow-up.

## Slide 12
Key Challenges and Executive Asks
The decision can move forward if these questions are explicitly owned
Bhawana Capital | LMS platform decision
12
Technology
Prototype is not deployed or scale-ready. Build path needs infra, SDLC, observability, and DWH integration.
Operations
Manual interactions remain. The platform must define who approves, who supports, and who escalates.
Scalability
Email-based process and ad hoc approvals will not scale across multiple LSPs without control automation.
Business
LSP motivation depends on lower effort, faster answers, better transparency, and clean integration.
Executive ask
Decision required
Owner
Build vs buy assessment
Approve criteria, timeline, and vendor shortlist.
Leadership
Prototype path
Decide whether prototype becomes MVP or remains learning artifact.
Product + Engineering
Operating model
Confirm RACI, manual approvals, support, and security gates.
Ops + Governance